## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to project | MUST HAVE | No Dependency | Bhavana Sri | 3- Completed
S1 | S1 | US-001 | About Statistical Models | MUST HAVE | No Dependency | Bhavana Sri | 2- In Progress
S1 | S1 | US-001 | Continuation of Statistical Models | MUST HAVE | No Dependency | Bhavana Sri | 3- Completed
S1 | S1 | US-001 | Chi-square test | MUST HAVE | No Dependency | Bhavana Sri | 3- Completed
S2 | S2 | US-001 | Explanation about NLP | MUST HAVE | Google colab | Bhavana Sri | 3- Completed
S3 | S3 | US-001 | How to load files to Notebook | MUST HAVE | Google colab | Bhavana Sri | 3- Completed
S3 | S3 | US-001 | Continuation of loading files | MUST HAVE | Google colab | Bhavana Sri | 3- Completed
S4 | S4 | US-001 | Introduction to RAG | MUST HAVE | Google colab | Bhavana Sri | 2- In Progress
S4 | S4 | US-001 | Introduction to LangChain | MUST HAVE | Google colab | Bhavana Sri | 2- In Progress
S4 | S4 | US-001 | Loading the Pdf file and introducing Groq API | SHOULD HAVE | Groq cloud | Bhavana Sri | 2- In Progress
S5 | S5 | US-001 | creating an API Token | MUST HAVE | Groq cloud | Bhavana Sri | 3- Completed
S5 | S5 | US-001 | Dividing to chunks and embeddings | MUST HAVE | Google colab | Bhavana Sri | 3- Completed
S6 | S6 | US-001 | Introducing the model and creating env file | MUST HAVE | Google colab | Bhavana Sri | 3- Completed
S6 | S6 | US-001 | Introduction to pandas AI agent | MUST HAVE | Google colab | Bhavana Sri | 3- Completed
S7 | S7 | US-001 | Implementing the Interface | MUST HAVE | Streamlit | Bhavana Sri | 2- In Progress
Note on F1: Mention the US ID(s) on which the user story depends. -Sumeet Kumar Barua08

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 33 | 2 | 0 | 1 | 1 | 3 | 6 | 3 | 2 | 3 | 2 | 3 | 4 | 2 | 1
SPRINT 1 BACKLOG
US-001 | TID-01 | Introduction to project | 2025-02-07 | 2025-02-08 | Sri Yaswitha Pradeepthi puvvada | Others | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-02 | About Statistical Models | 2025-02-09 | 2025-02-12 | Sri Yaswitha Pradeepthi puvvada | Build | 2- In Progress | 3 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-03 | Continuation of Statistical Models | 2025-02-13 | 2025-02-14 | Sri Yaswitha Pradeepthi puvvada | Build | 2- In Progress | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-04 | Chi-square test | 2025-02-14 | 2025-02-15 | Sri Yaswitha Pradeepthi puvvada | Others | 3- Completed | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-05 | Explanation about NLP | 2025-02-16 | 2025-02-18 | Sri Yaswitha Pradeepthi puvvada | Coding | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-06 | How to load files to Notebook |  | 2025-02-21 | Sri Yaswitha Pradeepthi puvvada | Coding | 2- In Progress | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-07 | Continuation of loading files | 2025-02-22 | 2025-02-23 | Sri Yaswitha Pradeepthi puvvada | Coding | 2- In Progress | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-08 | Introduction to RAG | 2025-02-24 | 2025-02-26 | Sri Yaswitha Pradeepthi puvvada | Others | 2- In Progress | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-09 | Introduction to LangChain | 2025-02-27 | 2025-03-05 | Sri Yaswitha Pradeepthi puvvada | Others | 2- In Progress | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0
US-001 | TID-10 | Introduction to pandas AI agent | 2025-03-06 | 2025-03-09 | Sri Yaswitha Pradeepthi puvvada | Coding | 2- In Progress | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
US-001 | TID-11 | Implementing the Interface | 2025-03-10 | 2025-03-14 | Sri Yaswitha Pradeepthi puvvada | Design | 3- Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1
Note on D2: 9/15/2016 or 15-Sep-2016 -Please enter the dates in either of these formats
Note on E2: 9/15/2016 or 15-Sep-2016 -Please enter the dates in either of these formats
Note on I3: This is the total task estimated in hours for all the user stories -Sumeet Kumar Barua08
Note on J3: Pending effort hours after completion of day 1 work -Sumeet Kumar Barua08
Note on K3: Pending effort hours after completion of day 2 work -Sumeet Kumar Barua08
Note on L3: Pending effort hours after completion of day 3 work -Sumeet Kumar Barua08
Note on M3: Pending effort hours after completion of day 4 work -Sumeet Kumar Barua08
Note on N3: Pending effort hours after completion of day 5 work -Sumeet Kumar Barua08
Note on O3: Pending effort hours after completion of day 6 work -Sumeet Kumar Barua08
Note on P3: Pending effort hours after completion of day 7 work -Sumeet Kumar Barua08
Note on Q3: Pending effort hours after completion of day 8 work -Sumeet Kumar Barua08
Note on R3: Pending effort hours after completion of day 9 work -Sumeet Kumar Barua08
Note on S3: Pending effort hours after completion of day 10 work -Sumeet Kumar Barua08
Note on T3: Pending effort hours after completion of day 11 work -Sumeet Kumar Barua08
Note on U3: Pending effort hours after completion of day 12 work -Sumeet Kumar Barua08
Note on V3: Pending effort hours after completion of day 13 work -Sumeet Kumar Barua08
Note on W3: Pending effort hours after completion of day 14 work -Sumeet Kumar Barua08

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint1 | Day 2 | Doubt about agile sheet | How to fill it asked to mentor
Sprint3 | Day6 | About How to upload all types of files | Make discussions
Sprint4 | Day9 | About Groq API key | How to create said by mentor
Sprint6 | Day20 | About Pandas AI agent | How to add agent
Sprint7 | Day 27 | About streamlit | Solved by the mentor

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint3 | 14-02-2025 | 20-02-2025 | Sri Yaswitha Pradeepthi puvvada | Loading pdf files | It is clear | Participation in meetings | Acheived Successfully
2 | Sprint4 | 21-02-2025 | 28-02-2025 | Sri Yaswitha Pradeepthi puvvada | RAG Implementation | completed | Asking to mentor if doubts | cleared
3 | Sprint5 | 2025-01-03 | 2025-07-03 | Sri Yaswitha Pradeepthi puvvada | Groq API Keys and Models | completed | Maintaining focus on keys | cleared
4 | Sprint6 | 2025-08-03 | 2025-11-03 | Sri Yaswitha Pradeepthi puvvada | Pandas AI agent | it is done | Code Implementation | Completed
5 | Sprint7 | 2025-12-03 | 14-03-2025 | Sri Yaswitha Pradeepthi puvvada | Interface Implementation | Completed | Completed | Completed
6
7